MONITORING, EVALUATION AND RESEARCH PLAN 2022

Name of office: UN Women Nepal Country Office

- Monitoring and Research Plan 2022

| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what Data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Source | Amount (USD) |
| Monitoring |  |  |  |  |  |  |  |  |  |  |
| Track the progress on SN output and outcome indicators using performance monitoring frameworks | N/A | N/A | N/A Bi-annual Partners’ reports | N | NCO, Rabin Rai | UN Women NCO | Semi-annual basis | N/A | N/A | Staff-time |
| Monitor support provided to the Ministry of Women, Children and Senior Citizens and other relevant ministries to develop, implement and monitor gender responsive plans, policies and programmes | SP Outcome 1 | NPL_D_1.1.1 | Indicator: NPL_D_1.1.1 A Quarterly partner’s report | N | NCO, Rachana Bhattarai | CSO partner | Q1 – Q4 2022 [Quarterly] | European Union (TBM) | Non-core | USD 500.00 |
| Monitor implementation of initiatives on GBV prevention and response | SP Outcome 4 | NPL_D_1.1.2 | Indicator: NPL_D_1.1.2 A Quarterly partner’s report | N | NCO, Kirti Thapa | CSO partner | Q1 – Q4 2022 [Quarterly] On-site field visits and periodic review meetings (remote) | Government of Finland | Non-core | USD 500.00 |
| Monitor implementation of initiatives with women's groups to mainstream gender in Disaster Risk Reduction (DRR) and preparedness | SP Outcome 1 and 5 | NPL_D_1.1.2 | Indicator: NPL_D_1.1.2 A NPL_D_1.1.3 A Quarterly partner’s report | N | NCO, Sama Shrestha |  |  | ECHO HIP | Non-core | USD 500.00 |
| Monitor gender mainstreaming in Provincial and Local Governance Support Programme (PLGSP) in collaboration with UNDP and UNCDF | SP Outcome 1 | NPL_D_1.1.2 | Indicator: NPL_D_1.1.2 A Quarterly partner’s report | N | NCO, Santosh Acharya | UNDP, Ministry of Federal Affairs and General Administration | Q1 – Q4 2022 [Quarterly] | Government of Finland | Non-core | USD 500.00 |
| Monitor the accompaniment support to women leaders at the local level in light of upcoming elections | SP Outcome 5 | NPL_D_1.1.2 | Indicator: NPL_D_1.1.2 A NPL_D_1.1.3 A Quarterly Partner’s report | N | NCO, Santosh Acharya | CSO partner | Q1 – Q4 2022 [Quarterly] | European Union (TBM) | Non-core | USD 500.00 |
| Monitor the implementation of initiatives on strengthening the capacity of key government officials in the justice sector at the sub-national level on substantive equality and gender-sensitive judicial procedures including local judicial committee | SP Outcome 1 and 4 | NPL_D_1.1.2 | Indicator: NPL_D_1.1.2 A Quarterly Partner’s report | N | NCO, Subha Ghale | CSO partner |  | Government of Sweden (TBM) | Non-core | USD 500.00 |
| Monitor the technical assistance provided to human rights institutions (NHRC/ NWC) on monitoring implementation of international/national GEWE commitments | SP Outcome 1 | NPL_D_1.1.2 | Indicator: NPL_D_1.1.2 A Quarterly Partner’s report NPL_D_1.1.2 B Quarterly Partner’s report Annual UPR report | N | NCO, Subha Ghale | National Human Rights Commission, National Women’s commission | Q1 – Q4 2022 [Quarterly] | Government of Finland European Union (TBM) | Non-core | USD 500.00 |
| Monitor the implementation of initiatives on strengthening women’s access to information in the context of COVID-19 | SP Outcome 4 | NPL_D_1.1.3 | Indicator: NPL_D_1.1.3 A Quarterly Partner’s report | N | NCO, Sama Shrestha | CSO partner | Q1 – Q4 2022 [Quarterly] | Government of Finland | Non-core | USD 1000.00 |
| Monitor the implementation of initiatives on addressing immediate short-term need of excluded groups including through women-led community Kitchen | SP Outcome 4 | NPL_D_1.1.3 | Indicator: NPL_D_1.1.3 A Quarterly Partner’s report | N | NCO, Anjana Vaidya |  |  |  |  |  |
| Monitor implementation of activities on strengthening community safety nets and feminist movement building in the COVID 19 context | SP Outcome 5 | NPL_D_1.1.3 | Indicator: NPL_D_1.1.3 A Quarterly Partner’s report | N | NCO, Rachana Bhattarai | CSO Partner | Q1 – Q4 2022 [Quarterly] | Government of Finland | Non-core | USD 1000.00 |
| Monitor implementation of initiatives on advancing the rights of women engaged in sex work | SP Outcome 5 | NPL_D_1.1.3 | Indicator: NPL_D_1.1.3 A Quarterly Partner’s report | N | NCO, Rachana Bhattarai |  |  |  |  |  |
| Monitor essential psycho-social and mental health support provided to women, youth and excluded groups in the COVID-19 context | SP Outcome 4 | NPL_D_1.1.3 | Indicator: NPL_D_1.1.3 A Quarterly Partner’s report | N | NCO, Palmu Sherpa |  | Q1 – Q4 2022 [Quarterly] | Government of Finland | Non-core | USD 500.00 |
| Monitoring of legal and accompaniment support provided to women facing intersecting forms of discrimination and GBV | SP Outcome 4 | NPL_D_1.1.3 | Indicator: NPL_D_1.1.3 A Quarterly Partner’s report | N | NCO, Kirti Thapa |  | Q1 – Q4 2022 [Quarterly] | Government of Finland |  |  |
| Monitor implementation of initiatives on strengthening capacities of women's organizations and networks on social accountability tools | SP Outcome 2 and 5 | NPL_D_1.1.3 | Indicator: NPL_D_1.1.3 A Quarterly Partner’s report | N | NCO, Palmu Sherpa |  | Q1 – Q4 2022 [Quarterly] | European Union (TBM) | Non-core | USD 500.00 |
| Monitoring of support provided for community mobilization efforts with women from excluded groups, their families, members and leaders of communities, and decision-makers to challenge adverse social norms and structural barriers to women’s economic empowerment (agriculture value chain) | SP Outcome 3 | NPL_D_2.1.1 | Indicator: NPL_D_2.1.1 B Indicator: NPL_D_2.1.1 C Annual programme report | Y, NCO will conduct dedicated research on social norm change using storytelling methodology to collect data on these indicators. | NCO, Santosh Acharya | CSO Partner |  | European Union (TBM) | Non-core | USD 500.00 |
| Monitoring of comprehensive package, peer support and re-skilling support provided to women (storytellers) at the community level | SP Outcome 4 and 5 | NPL_D_2.1.1 | Indicator: NPL_D_2.1.1 G NPL_D_2.1.1 H Quarterly Partner’s report | Y, NCO will conduct dedicated research on social norm change using storytelling methodology to collect data on these indicators. | NCO, Ashma Shrestha |  | Q1 – Q4 2022 [Quarterly] | Government of Finland | Non-core | USD 1000.00 |
| Monitor implementation of initiatives on strengthening knowledge and capacities of key stakeholders on gender responsive macroeconomic policies to promote decent employment and investments in care | SP Outcome 1 and 2 | NPL_D_2.1.2 | Indicator: NPL_D_2.1.2 A Annual programme reports/Government reports | N | NCO, Priti Shrestha | CSO Partner, Research Agency | Q1 – Q4 2022 [Quarterly] | ILO JP/Swiss | Non-core | USD 500.00 |
| Monitor implementation of the pilot initiative on financial inclusion in province 7 | SP Outcome 4 | NPL_D_2.1.3 | Indicator: NPL_D_2.1.3 B Quarterly Partner’s report | N | NCO, Santosh Acharya | CSO Partner |  | Government of Finland | Non-core | USD 500.00 |
| Monitor implementation of capacity development support provided to women and excluded groups to enhance their leadership skills to access their rights, entitlements and resources (including financial services, disaster and climate smart tools, technologies and information) and | SP Outcome 4 and 5 | NPL_D_2.1.3 | Indicator: NPL_D_2.1.3 A Annual programme reports/Government reports | N | NCO, Rachana Bhattarai | CSO Partner |  | Government of Finland | Non-core | USD 500.00 |
| Support monitoring of UNDAF 2018 - 2022 | UNDAF Outcome 4 (as co-chair) | NPL_O_1.1 | NPL_O_1.1A | Y, UNDAF Annual Reporting and GE Scorecard | NCO, Navanita Sinha | UNDAF Outcome Groups | Q4 | N/A | N/A | Staff time |
| Research |  |  |  |  |  |  |  |  |  |  |
| NPL_D_1.1.1.2: Undertake research on Violence against Women in Politics | SP Outcome 5 | NPL_D_1.1.1 | Indicator: NPL_D_1.1.1 A Research/Study Annual | Y, the research itself will collect the data. | NCO, Santosh Acharya | CSO and government partner | Q1-Q2 | Government of Finland | Non-core | USD 25,000.00 |
| NPL_D_1.1.1.2: Undertake a survey on experiences of discrimination and violence on LGBTIQ+ | SP Outcome 5 | NPL_D_1.1.1 | Indicator: NPL_D_1.1.1 A Survey Annual | Y, the research itself will collect the data. | NCO, Subha Ghale | M & C Saatchi in consortium with BDS Nepal and Viamo [other stakeholders MoWCSC, CSOs] | Q1-Q3 | Government of Finland | Core and Non-core | USD 117,338 [Core- USD 61,000.00 Government of Finland- USD 56,338.00] |
| NPL_D_1.1.1.2: Conduct rapid assessment of GBV prevention initiatives in Nepal | SP Outcome 3 and 5 | NPL_D_1.1.1 | Indicator: NPL_D_1.1.1 A Research/Study Annual | Y, the data will be collected through research itself. | NCO, Kirti Thapa | UNICEF | Q1-Q2 | Core and EU | Core and Non-core (EU) | USD 15,000 |
| NPL_D_1.1.2.2 Conduct research on impact of COVID 19 on access to justice of women and excluded groups, including e-justice | SP Outcome 4 and 5 | NPL_D_1.1.2 | Indicator: NPL_D_1.1.2 A Research/Study Annual | Y, the data will be collected through research itself. | NCO, Subha Ghale | CSO partner | Q1-Q4 2022 | Government of Sweden | Non-core | USD 40,500.00 |
| NPL_D_1.1.3.1: Conduct research on measuring social norm change through storytelling | SP Outcome 3 and 5 | NPL_D_1.1.3 | Indicator: NPL_D_1.1.3 D Survey Alternate years (over five years period) | Y, the data will be collected through research itself. | NCO, Ashma Shrestha | Research Agency, Government of Finland | Q1-Q4 2022 | Government of Finland | Non-core | USD 170,000.00 |
| NPL_D_2.1.1.1 Conduct perception survey on attitudes and practices of communities towards Women’s Economic Empowerment and Leadership (end line data for current SN) | SP Outcome 3 and 5 | NPL_D_2.1.2 | Indicator: NPL_D_2.1.2 A Research/Study Annual | Y, the data will be collected through research itself. | NCO, Santosh Acharya | CSO Partner, Research Agency | Q2-Q3 2022 | Government of Finland | Non-core | USD 40,000.00 |
| NPL_D_2.1.2.1: Conduct expenditure review from a gender lens at sub-national level focusing on women and most excluded communities; | SP Outcome 2 | NPL_D_2.1.2 | Indicator: NPL_D_2.1.2 A Research/Study Annual | Y, the data will be collected through research itself. | NCO, Priti Shrestha | CSO Partner, Research Agency UN agencies (UNDP and UNCDF) | Q2-Q3 2022 | MPTF SDG | Non-core | USD 50,000.00 |

- Evaluation Plan 2022

| Evaluation name | Mandatory? (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/Relevant flagship program | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Country Portfolio Evaluation | Y | N/A | Indicator: OEE NPL_O_3.1 | NCO | Nepal | N | Q1 – Q3 | USD 33,000 [core: USD 8,000 and Government of Finland: USD 25,000] |  | This will be led by IES with support from NCO. |
| Developmental Evaluation Phase III | N | N/A | Indicator: OEE NPL_O_3.1 | NCO | Nepal | N | Q1 | USD 3,000 [Core] |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |
| Evaluation of UNDAF 2018-2022 | Y | N/A | Indicator: OEE NPL_O_3.1 | UN RCO | Nepal | Y | Q1 | N/A |  | Initiated in 2021 and led by UNRCO and UN Women is part of the Evaluation Management Team. |

Please fill out a separate row for each evaluation.

UN Sustainable Development Cooperation Framework (UNSDCF), formerly known as UNDAF.

Outcomes contributing to the SDGs as per the Strategic Plan