COLOMBIA COUNTRY OFFICE

MONITORING, EVALUATION AND RESEARCH PLAN 2021-2024 (update March, 2024)

Monitoring 2021-2024

| UNSDCF Outcome/UN Women SP Outcome/SN output | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| UNSDCF outcomes included in UN Women SN and related outputs; relevant SP outcomes; | Reports on the UNSDCF (4W system, JWPs, UNSDCF M&E framework, UNINFO; COVID UNCT response, programme criticality, Government; etc.) | UNW Planning and M&E team (PME) | RCO, UN Agencies focal points and UNCT | Every semester and upon request (frequent) | Non-Core (Sweden/Norway) | 2,000 each |
| UNSDCF outcomes included in UN Women SN and related outputs; relevant SP outcomes; | Annual report, mid-term and final report on the Cooperation Framework 2021-24 between UN Women and the Government of Colombia. | UNW PME team | Ministry of Foreign Affairs, Key institutional partners of UN Women in Colombia | March 2020, 2021, 2022, 2023 and 2024. Mid 2023, and December 2024. | Non-Core (Sweden/Norway/FPI stats) | 2,000 each |
| UNSDCF priority area 2; SN outcome 2 and related outputs | GIFMM information system and other related requests and reporting system | UNW PME team/migration team | Key migration stakeholders | Every semester and upon request (frequent) | Non-core (U.S. State Department) | 2,000 each |
| All SN (DRF and OEEF); relevant SP outcomes; | Quarterly monitoring of activities - Progress Reports RMS. Quantum reporting | UNW PME team | Corporate – CO - Regional Office | Every quarter 2021-2024 | Non-Core (Sweden) | $10,000 per year |
| All SN (DRF and OEEF); relevant SP outcomes | Annual Report AWP | UNW PME team | Corporate - CO - Regional Office | Every January 2021-2024 | Non-Core (Sweden/Norway) | $5,000 per year |
| All SN outcomes and outputs; relevant SP outcomes | Narrative and financial project reports to Donors as per DAMS reporting commitments | UNW PME team and programme teams | Corporate - CO - Regional Office, donors | As per DAMS commitments | Non-Core (different sources as per project portfolio and related DAMS commitments) | As per each project budget |
| UNSDCF/SN priority area 3 (outcome 3.1, output 3.1.1) | Narrative and financial project reports to Donor (Project Women Count) | UNW PME team (statistics team) | Corporate - CO - Regional Office, HQ Women Count | First quarter 2021, 2022 and 2023 | Non-Core (TBD) | 2,000 each |
| UNSDCF/SN priority area 1 and 3 (outcomes 1.2 and 3.2, multiple outputs) | Narrative and financial project reports to WPHF, MPTF and bilateral donors on call for proposals for CSOs | UNW PME team (technical secretariat for CSOs call for proposals) | Corporate - CO - Regional Office, HQ WPHF | First quarter of each year and upon request | Non-Core (WPHF, Norway, Germany, Koica, etc.) | $5,000 |
| All SN outcomes and outputs; relevant SP outcomes | Other progress reports, monthly and quarterly updates (e.g. for U.S. State Department, INL, Norway, etc.) not included in DAMS (non-formal reporting commitments) | UNW M&E focal point / Programme Manager | Corporate - CO - Regional Office | As per donors and partners requests | Non-Core (different sources as per project portfolio and related DAMS commitments: e.g. U.S. State Department, INL, Norway, etc) | $5,000 |

Research Plan 2021-2024

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Colombia's Progress in Public Procurement with a Gender Approach | UN WOMEN – Colombia Compra Eficiente y Consejería Presidencial para la Equidad de la Mujer | June - July, 2021 | Non-Core (USAID) | $ 10,000 |
| Systematization of the legislative agenda with a gender perspective. | UN WOMEN – Comisión Legal para la Equidad de la Mujer | June - July, 2021 | Non-Core (Sweden) | $15,000 |
| Third measurement of the Study of social and institutional tolerance to violence against women, (national and for the Meta, Cauca and Antioquia) | UN WOMEN – Consejería Presidencial para la Equidad de la Mujer | July – August, 2021 | Non-Core (USAID) | $70,000 |
| Project transmedia Ruta 2020: Documentary on women, peace and security | UN WOMEN | October, 2021 | Non-Core (Sweden) | $40,000 |
| Second edition (2021) and third edition (2024) of "Women and men: gender gaps in colombia (gender national profile)" and other knowledge products FPI Women Count gender profile Nariño, Cauca, Meta and Antioquia | ONU MUJERES – Departamento Administrativo Nacional de Estadística – Consejería Presidencial para la Equidad de la Mujer and Gobiernos locales | October, 2022, 2023, 2024 | Non-core (Sweden) FPI Women Count | $40,0000 |
| Ten-year analysis and trends of gender related killings of women and feminicides in Colombia, FPI Women Count. | UN Women | November, 2021 or 2022 | Non-core (Sweden) FPI Women Count | $15,000 |
| Rapid Gender Assessments (RGA), on issues such as disability, violence against women, migration, etc.. | ONU MUJERES – Departamento Administrativo Nacional de Estadística – Consejería Presidencial para la Equidad de la Mujer and Gobiernos locales | August and December, 2021, 2022, 2023, 2024 | Non-core (UNPRPD) FPI Women Count | $25,000 and other funding TBD |
| Development of new Knowledge Management Strategy | UN WOMEN | 12/2023 - 5/2024 | Core | 13,000 |
| Knowledge products related to priority area 1 of the UNSDCF/SN developed by WPS team. Focus on promotion of women's participation and leadership in peace agreements’ implementation, reincorporation, post-conflict and natural disasters, including KM activities and products developed by the Technical Secretariat for competitive funding for civil society (WPHF, Norway) | UN WOMEN (mainly WPS team) | 1/2021 - 12/2021 1/2022 - 12/2022 1/2023 - 12/2023 1/2024 - 12/2024 | Non-Core (Sweden, Norway, WPHF) | $20,000 per year |
| Knowledge products related to priority area 3 of the UNSDCF/SN developed by SDG team with the support of PME/statistics team. Focus on women's leadership and participations in decision-making processes at local, municipal, regional and national level in Colombia, care work and women’s economic empowerment, GBV, etc. | UN WOMEN (mainly SDG team) | 1/2021 - 12/2021 1/2022 - 12/2022 1/2023 - 12/2023 1/2024 - 12/2024 | Non-Core (Sweden, Koica, Canada and other TBD) | $15,000 per year |
| Knowledge products related to priority area 2 of the UNSDCF/SN developed by migration team in partnership with PME/statistics team. Focus on the assessments of migrant women and host communities situation, migrants women economic empowerment, etc. | UN WOMEN (mainly migration team) | 1/2021 - 12/2021 1/2022 - 12/2022 1/2023 - 12/2023 1/2024 - 12/2024 | Non-Core (U.S. State Department and Swiss Cooperation) | $20,000 per year |

Evaluation Plan 2021-2024

| Evaluation name | Mandatory? (Y/N) | UNSCDF Outcome/ UN Women SP Outcome, and relevant SDGs | SN Output/ Relevant flagship program | Office and person in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Donors involved | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation USAID project: End GBV | Y | UNSDCF out 3.2; UN WOMEN SP 3; SDG 1; SDG 5; SDG 8; SDG 16 and SDG 17 | Colombia SN priority area 3 (outcome 3.2, specific output UNW) | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | N | USAID | 05-21 to 9-21 | 20,000 Non-Core | Completed | None |
| Mid-term evaluation Safecities (Medellín) | N | UNSDCF out 3.2; UN WOMEN SP 3; SDG 1; SDG 5; SDG 8; SDG 16 and SDG 17 | Colombia SN priority area 3 (outcome 3.2, specific output UNW) | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | N | AECID and local governments (mainly Medellín) | 7-21 to 11-21 | 15,000 non-core | Completed | None |
| Final evaluation PBF binational programme (joint with UNW Ecuador. Procurement process led by UNW Ecuador) | Y | UNSDCF out 1.2; UN WOMEN SP 4; SDG 1; SDG 5; SDG 8; and SDG 16 | Colombia SN priority area 1 (output 1.2.4) | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | Y (UNW, UNICEF, UNHCR) | PBF | 12/20-2/21 | 5,000 non-core (UNW Col part) | Completed | None |
| Final evaluation Prodefensoras programme | Y | UNSDCF out 3.5; UN WOMEN SP 4; SDG 1; SDG 5; SDG 8; and SDG 16 | Colombia SN priority area 1 (output 3.5.1) | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | N | Norway | 7/22 to 12/22 | 12,000 Non-core | Completed |  |
| Evaluation/internal review PRM programme portfolio | Y | UNSDCF priority area 2 | SN priority area 2 | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | N | State Department | 6-9/24 | 10,000 non core | Pending | TBC. Under discussion the possibility of internal review exercise |
| Evaluation of Sweden non-earmarked contribution to the SN (evaluation of the model/type of support) | Y | UNSDCF outcomes included in UN Women SN and relevant SP outcomes; SDG 1; SDG 3; SDG 5; SDG 8; SDG 16 and SDG 17 | All | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | N | Sweden | 11/22 to 5/23 | 17,000 Non-core | Completed | Being an evaluation of the non-earmarked support to the SN, this process has covered a broad portfolio of the CO and can be considered similar to a formal evaluation of the SN |
| Final evaluation of new agreements with Sweden | Y | TBD | TBD | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | N | Sweden | 5/2027 | 10/2027 | Pending | Subject to projects’ approval |
| Final evaluation of phase 2 Prodefensoras | Y | UNSDCF out 3.5; UN WOMEN SP 4; SDG 1; SDG 5; SDG 8; and SDG 16 | Colombia SN priority area 1 (SN output 1.3.1) | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | Y | Norway | 7/2025 | 11/2025 | Pending |  |
| Formative evaluation of UN Women Colombia humanitarian portfolio with a focus on livelihoods | N | UNSDCF out 3.5 and priority area 2; UN WOMEN SP 4; SDG 1; SDG 5; SDG 8; and SDG 16 | Colombia SN priority area 1 and 2 (output 3.5.5 and all outputs of outcome 2) | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | N | CO, TBD (e.g. WPHF, CERF, etc.) | TBD | 25,000 non-core | Pending | Subject to funds availability |
| Formative evaluation on the institutional use of the gender budgeting tracker | N | UNSDCF outcome 3.2; SP 2 SDG 5 | SN output 3.2.2 | Colombia/Planning, Monitoring and Evaluation (PME) team | Colombia | N | Canada | 1-5/2024 | 15,000 non- core (Canada) | Ongoing |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Formative Corporate Evaluation: UN Women's support for capacity development of partners |  | N/A | N/A | IES (Florencia Tateossian) | Global | N |  |  |  | Completed | Colombia case study |
| UN Women global evaluation on political participation |  | Outcome 3.2 | SN outcome 3.2 | IES | Global |  |  |  |  | Ongoing | Colombia case study |
| UN Women Regional evaluation on civil society engagement |  | All | All | IES | Regional |  |  |  |  | Ongoing |  |
| UN Women Global evaluation on WPS 2018-2023 |  | 1 | All under outcome 1 | IES | Global |  |  | 3/2024 (case study) | 5/2024 (case study) | Ongoing | Colombia case study |
| External global evaluation WPHF |  | 1 | All under outcome 1 | WPHF (Erica Stillo) | Global |  | WPHF | 3/2024 (case study) | 5/2024 (case study) | Ongoing | Colombia case study |
| UNSDCF Final evaluation | Y | ALL UNSDCF outcomes; all SDGs aligned to UNSDCF | All UNSDCF | RCO together with UN Women (advisor-planning and M&E coordinator) and UNODC | Country | Y | UN Presidential Agency for Cooperation Ministry of Foreign Affairs | Feb 2023/Nov 2023 | 45,000 | Completed | UN Women co-leads the evaluation and given the full alignment of the SN with the UNSDCF, provides key findings also related to the SN |
| Final evaluation of UN MPTF (SDG-F, etc.) funded joint programmes | Y | TBD | TBD | Lead agency | Colombia | Y (TBD) | UN MPTF (SDG-F, etc.) | TBD | TBD | Pending | Subject to projects’ approval |

In order to ensure stronger thematic alignment, UNSDCF outcome 3.5 is included in the SN under priority area 1.

In order to ensure stronger thematic alignment, UNSDCF outcome 3.5 is included in the SN under priority area 1.