MONITORING, EVALUATION AND RESEARCH PLAN 2021-2022 : Argentina

Monitoring and Research Plan 2021-2022

| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |  |  |  |  |
| Monitoring Country Programme | OEE Output 2 | Argentina AWP OEEF Output 2.1 | 0.5.A | Y (TBD) | UN Women Argentina Veronica Baracat |  | Year 2022 |  |  |  |
| RESEARCH |  |  |  |  |  |  |  |  |  |  |
| Research studies and analyses on GBV and femicide to influence on public decision making and on strengthening / adjusting the regulatory framework (Spotlight) | Impact 3 Outcome 3.1 (SDG 5.2.1) | Argentina AWP Output 3.1.4 |  | Y Qualitative study on the quality of services for GBV survivors in rural areas of the province of Salta Final Report Available here | Argentina- Carla Majdalani | Fundación Markani (CSO) Ministry of Human Rights (Salta) | August 2020- May 2021 | MPTF-Spotlight EU | Non- Core | USD 45.000 |
|  | Impact 3 Outcome 3.1 (SDG 5.2.1) | Argentina AWP Output 3.1.4 |  | Y Research Study on the implementation of Law 27.452 (Economic reparation for collateral victims of femicide) Final report available Here | Argentina Carla Majdalani | Universidad Nacional de Río Negro | July 2020- March 2021 | MPTF-Spotlight EU | Non- Core | USD 3.800 |
|  | Impact 3 Outcome 3.1 (SDG 5.2.1) | Argentina AWP Output 3.1.4 |  | Y Study on legal protection for GBV survivors in 11 provinces Final report available here | Argentina Carla Majdalani | ELA / Fondo de Mujeres del Sur | June 2020- January 2021 | MPTF-Spotlight EU | Non- Core | USD 5000 |
|  | Impact 3 Outcome 3.1 (SDG 5.2.1) | Argentina AWP Output 3.1.4 |  | Y Data collection on legislative initiatives addressing GBV in 6 provinces Final report available here | Argentina Carla Majdalani | ELA / Fondo de Mujeres del Sur | June 2020- January 2021 | MPTF-Spotlight EU | Non- Core | USD 5000 |
| Research studies and analyses targeted at making informed decisions (Spotlight) | Impact 3 Outcome 3.1 (SDG 5.2.1) | Argentina AWP Output 3.1.4 |  | Y Base line study on reporting channels for GBV survivors at police stations in 8 provinces Final report available here | Argentina Carla Majdalani | UNLP (Universidad Nacional de La Plata) Ministry of Security | December 2020- May 2021 | MPTF-Spotlight EU | Non-core | USD 30.000 |
| Research Business case – How does a brand's incorporation of gender perspective impact on sales of a company? (Win-win) | Impact 2 Outcome 4. | Argentina AWP Outcome 2.1. | SP 2018-2021 | Y (on-line surveys) | Argentina – Veronica Baracat | Interbrand (vendor) | 2021 | European Union | Non Core | Usd 25,000 |
| Generate evidence on the socioeconomic impact of the COVID -19 pandemic on the care economy, focusing on older persons and people with disabilities (MPTF) | Impact 2 Outcome 2.2 | Argentina AWP Output 2.2.1 | 0.4a |  | Argentina Sabrina Landoni | National Institute of Social Services for Retirees and Pensioners | 04/21 – 12/21 | MPTF-UN COVID-19 Response Rcvy | Non-Core | USD 16,500 |
| Develop a care map (centres and services) for older persons and people with disabilities (MPTF) | Impact 2 Outcome 2.2 | Argentina AWP Output 2.2.1 | 0.4a |  | Argentina Sabrina Landoni | Ministry of Women, Gender and Diversity | 06/21 – 12-21 | MPTF-UN COVID-19 Response Rcvy | Non core | USD 10000 |
| Tool of Gender Fiscal Stimulus Package in Argentina | Impact 2 Outcome 2.2. | Argentina AWP Output 2.2.1. | O.4.a O.7.c | Y | Argentina Gimena de León | CIEPP | 10/21-04/22 | OSF | Non core | USD 20000 |
| Customize policy interventions according to national priorities to promote Gender Responsive Fiscal Stimulus Packages in Argentina | Impact 2 Outcome 2.2. | Argentina AWP Output 2.2.1. | O.4.a O.7.c | Y | Argentina Gimena de León | CIEPP | 01/22-05/22 | OSF | Non core | USD 10000 |
| Expanding existing costing exercise of Care Policies in Argentina. | Impact 2 Outcome 2.2. | Argentina AWP Output 2.2.1. | O.4.a O.7.c | Y | Argentina Gimena de León | CIEPP | 03/22-08/22 | OSF | Non core | USD 20000 |
| Qualitative study on femicides in Salta and Jujuy (2016/2020) | Impact 3 Outcome 3.1 (SDG 5.2.1) | Argentina AWP Output 3.1.4 | Indicator 0.33 Qualitative Study 2022 | Y | Argentina Carla Majdalani | UNDP Spotlight Coordination Unit Supreme Court of Justice Goverments of Salta and Jujuy | 1/22 - 9/22 | MPTF-Spotlight EU | Non Core | $23.000 |
| Document identifying viability conditions of businesses to women and LBTIQ population as contractors of public infrastructure. | Impact 2 Outcome 2.1 | Argentina AWP Output 2.1.2 | Indicator 0.4a |  | Argentina Lisa Solmirano | CISCSA | 01/22-10/22 | MOP | Non-Core | $10,000 |
| Set of 4 Manuals to include gender perspective in the design and execution of public infrastructure | Impact 2 Outcome 2.1 | Argentina AWP Output 2.1.2 | Indicator 0.4a |  | Argentina Lisa Solmirano | UNW UNOPS Ministry of Public Infrastructure | 11/21 -12/22 | MOP | Non-Core | 40,000 |

Evaluation Plan 2021-2022

| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations led by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| One Win Leads to Another Programme final evaluation | YES | SDG 5, Outcome 4: All women and girls live a life free from all forms of violence | Argentina AWP Output 3.2 | UN Women Argentina | Latin America and the Caribbean | NO | September 2021-December 2021 | COI | 23,000 Non-core funds (Program Budget: donor: IOC) | Initiated | To be completed in December 2021 |
| Final report “Support to the Argentinean Government” | Yes | SDG 5 (all support in all SDGs) | Argentina AWP Impact 6 | UN Women Argentina Veronica Baracat | Latin America and the Caribbean | No | June 2022 | Government of Argentina (GoA) | Staff Time | Pending |  |
| Women Economy Autonomy – MPTF final report | Yes | SDG 5, SDG 8, SDG 10 | Argentina AWP Output 2.2 | UN Women Argentina Sabrina Landoni | Latin America and the Caribbean | Yes: ILO, UNPD, ECLAC | January- 2022 - March 2022 | MPTF | $12981 (Non-Core Donor MPTF) | Pending |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |
| Joint Final Evaluation of Programme Win Win: gender equality means good business | YES | SDG 5, SDG 8, SDG 10, SDG 27 Impact 2, Outcome 3: Women have income security, decent work and economic autonomy | Argentina AWP, Output 2.1. | ACRO LAC | Latin America and the Caribbean | YES: ILO | August 2021 | European Union | $100,000 Non-core (EU) | Finished |  |
| Spotlight Initiative final evaluation | Yes | SDG 5, Outcome 4: All women and girls live a life free from all forms of violence | Argentina AWP Output 3.2 | UN Women Argentina Carla Majdalani | Latin America and the Caribbean | YES: ILO, UNDP, UNFPA, RCO | November 2022-December 2022 | MPTF-Spotlight EU | $21629 Non- Core Donor MPTF-Spotlight EU | Finished | Final report and summary available here |

Please fill out a separate row for each evaluation.

Outcomes contributing to the SDGs as per the Strategic Plan